## Instructions
Construction Budget Template
Purpose
This workbook tracks a construction job's budget from original estimate through completion: enter your cost codes, original budget, committed cost (subcontracts and POs), and actual cost to date, log change orders as they happen, and get a one-page dashboard with cost-to-complete and projected final cost by division. Replace the sample cost codes and figures with your own — every formula recalculates automatically.
Clean-room disclosure
Clean-room disclosure: every formula, layout, and sample figure in this workbook was authored from scratch for excel.tv. No vendor workbook, template, branding, or sample dataset was downloaded, inspected, or adapted in building this file. All data shown is synthetic and for illustration only.
What’s in this workbook
Cost Codes |  | The master list of cost codes (code, division, description, notes). Add, remove, or rename cost codes here — the rest of the workbook looks up from this list.
Budget Input |  | Enter the original budgeted amount for each cost code, set at the start of the job.
Committed Cost Input |  | Enter the committed cost for each cost code — the subcontract or purchase order value, whether or not it has been fully paid yet.
Actual Cost Input |  | Enter the actual cost paid to date for each cost code, plus any additional anticipated cost not yet covered by a committed contract.
Change Orders |  | Log every change order with its cost code, status, and amount. Only Approved change orders flow into the revised budget.
Budget vs Committed vs Actual |  | Automatically compares original budget, approved change orders, committed cost, actual cost, cost-to-complete, and variance for every cost code. Nothing on this sheet needs to be typed in.
Dashboard |  | The one-page summary: pick a division to drill into, and see project-wide totals for budget, committed, actual, cost-to-complete, and projected over/under, plus the cost codes flagged for review.
How to use this workbook
1. Open the Cost Codes sheet and edit the list to match your own job (keep each Cost Code unique).
2. Open Budget Input and enter the original budgeted amount for each cost code.
3. Open Committed Cost Input and enter the committed subcontract or PO value for each cost code as contracts are signed.
4. Open Actual Cost Input and enter the actual cost paid to date for each cost code, updating it as invoices are paid.
5. Log every change order on the Change Orders sheet as it comes in, and mark its status Approved, Pending, or Rejected.
6. Go to the Dashboard sheet and use the division selector to review one division at a time, or read the project totals for the whole job.
Colour legend
Colour legend
Input — enter or edit your own data here
Calculated — formula-driven, please do not overwrite
Output — key result for reporting and dashboards
Using this workbook in Google Sheets
To use this workbook in Google Sheets: open Google Sheets, choose File > Import > Upload, select this .xlsx file, and choose "Insert new sheet(s)". Every formula in this workbook (SUM, SUMIF, SUMIFS, IF, IFERROR, INDEX, MATCH, ABS, ROUND, LARGE) is natively supported in Google Sheets, so no formula substitutions are required. Dropdown data validation on the division selector also carries over automatically.
Limitations
This template assumes each cost code is unique and appears exactly once on the Cost Codes, Budget Input, Committed Cost Input, and Actual Cost Input sheets. Cost-to-complete is calculated as the greater of (committed cost minus actual cost to date) or zero, plus a manually entered "additional anticipated cost" for scope beyond what is currently committed — it is only as accurate as that manual estimate, so update it as a job progresses. Only change orders marked Approved on the Change Orders sheet flow into the revised budget; Pending change orders are visible in the log but do not change any total until you flip their status. The 5% review-flag threshold on the Budget vs Committed vs Actual sheet is a fixed sample value — change the flag formula there if your job uses a tighter or looser tolerance. No macros, no external connections — everything here is a native formula, which is what keeps the workbook portable between Excel and Google Sheets with zero substitutions.
★ Free template from Excel.TV — get more free Excel & Google Sheets templates →

## Cost Codes
Cost Code | Division | Description | Notes
01-100 | General Conditions | Permits, Fees & Inspections | Building permit, plan review, and inspection fees paid to the local jurisdiction.
01-200 | General Conditions | Supervision & Project Management | Superintendent and PM time for the full duration of the job.
02-100 | Sitework | Site Clearing & Grading | Clearing, rough grading, and building pad prep before foundation work starts.
02-200 | Sitework | Erosion & Sediment Control | Silt fence, inlet protection, and stabilization required by the site permit.
03-100 | Concrete | Footings & Foundation Walls | Poured footings and foundation walls, including rebar and formwork.
03-200 | Concrete | Slab on Grade | Garage and basement slab pour, including vapor barrier and control joints.
06-100 | Framing | Rough Framing Labor | Framing crew labor for walls, floors, and roof structure.
06-200 | Framing | Framing Materials & Lumber | Dimensional lumber, engineered joists, and sheathing for the full frame.
09-100 | Finishes | Drywall, Insulation & Paint | Insulation, drywall hang/finish, and interior paint across the house.
09-200 | Finishes | Flooring | Hard-surface and carpet flooring for all finished rooms.
09-300 | Finishes | Cabinetry, Countertops & Trim | Kitchen and bath cabinetry, countertops, and interior trim/millwork.
15-100 | MEP | Plumbing Rough-In & Fixtures | Supply/drain rough-in plus fixture sets for kitchen and baths.
15-200 | MEP | HVAC System Installation | Furnace, condenser, ductwork, and controls for the full house.
16-100 | MEP | Electrical Rough-In & Panel | Service panel, rough wiring, and device rough-in for the full house.

## Budget Input
Enter the original budgeted amount for each cost code below, set at the start of the job. Description is looked up automatically from Cost Codes — do not type into that column.
Cost Code | Description | Original Budget
01-100 |  | 6500
01-200 |  | 27000
02-100 |  | 18000
02-200 |  | 4200
03-100 |  | 32000
03-200 |  | 14500
06-100 |  | 41000
06-200 |  | 52000
09-100 |  | 24000
09-200 |  | 16800
09-300 |  | 31000
15-100 |  | 22500
15-200 |  | 28000
16-100 |  | 19500

## Committed Cost Input
Enter the committed cost for each cost code below — the signed subcontract or purchase order value, whether or not it has been fully invoiced yet. Description is looked up automatically from Cost Codes.
Cost Code | Description | Committed Cost
01-100 |  | 6500
01-200 |  | 27000
02-100 |  | 18500
02-200 |  | 4200
03-100 |  | 35800
03-200 |  | 14200
06-100 |  | 44200
06-200 |  | 55600
09-100 |  | 24000
09-200 |  | 21900
09-300 |  | 31000
15-100 |  | 23100
15-200 |  | 28000
16-100 |  | 20100

## Actual Cost Input
Enter the actual cost paid to date for each cost code, plus any additional anticipated cost not yet covered by a committed contract (for example, scope you know is coming but haven't subcontracted yet). Description is looked up automatically from Cost Codes.
Cost Code | Description | Actual Cost to Date | Additional Anticipated Cost
01-100 |  | 6100 | 0
01-200 |  | 18400 | 8600
02-100 |  | 18500 | 0
02-200 |  | 4200 | 0
03-100 |  | 35800 | 0
03-200 |  | 14200 | 0
06-100 |  | 38900 | 1200
06-200 |  | 55600 | 0
09-100 |  | 9600 | 0
09-200 |  | 8200 | 0
09-300 |  | 6200 | 0
15-100 |  | 19800 | 0
15-200 |  | 11200 | 2600
16-100 |  | 20100 | 0

## Change Orders
CO # | Cost Code | Description | Status | Amount | Date
CO-001 | 03-100 | Unforeseen rock excavation required deeper footings on the north wall. | Approved | 4200 | 2026-02-10
CO-002 | 06-100 | Owner-requested bonus room over the garage added to the framing scope. | Approved | 3800 | 2026-03-18
CO-003 | 15-200 | Upgrade to a higher-efficiency variable-speed HVAC system. | Pending | 2600 | 2026-04-02
CO-004 | 09-200 | Change from engineered vinyl plank to solid hardwood in the main living areas. | Approved | 5100 | 2026-04-22
CO-005 | 02-100 | Additional grading for unexpected soil conditions at the building pad. | Rejected | 1900 | 2026-01-29

## Budget vs Committed vs Actual
Cost Code | Division | Description | Original Budget | Approved COs | Revised Budget | Committed | Actual to Date | Cost to Complete | Projected Final Cost | Variance $ | Variance % | Overrun $ | Flag (1/0) | Status

## Dashboard
Construction Budget Template
Select division to review: | Framing
Selected division — cost snapshot
Original Budget
Approved Change Orders
Revised Budget
Committed Cost
Actual Cost to Date
Cost to Complete
Projected Final Cost
Variance $ (Revised Budget − Projected Final Cost)
Variance %
Project totals — every division
Total Original Budget
Total Approved Change Orders
Total Revised Budget
Total Committed Cost
Total Actual Cost to Date
Total Cost to Complete
Total Projected Final Cost
Projected Over / (Under) Budget
Projected Over / (Under) Budget %
Review flags & change order log
Cost codes flagged for review (>5% variance):
Total Rejected Change Orders ($):
Total Pending Change Orders ($):
Top 3 cost overruns (by $ over budget, project-wide)
Rank | Cost Code | Description | Overrun $
1
2
3
★ Free template from Excel.TV — get more free Excel & Google Sheets templates →