## Instructions
Construction Schedule Template
Purpose
This workbook builds a construction schedule of works from a simple task list: enter each task, the trade responsible, its duration in calendar days, and which earlier task it starts after, and the workbook chains every Start and Finish date automatically. Change one task's duration or predecessor and every downstream date recalculates, the weekly Gantt grid redraws itself, and the trade dashboard updates. Replace the sample tasks with your own — every formula recalculates automatically.
Clean-room disclosure
Clean-room disclosure: every formula, layout, and sample figure in this workbook was authored from scratch for excel.tv. No vendor workbook, template, branding, or sample dataset was downloaded, inspected, or adapted in building this file. All data shown is synthetic and for illustration only.
What’s in this workbook
Project Setup |  | The project name, the project start date, the "as of" date used to compute task status below, and the master list of trades used by the dropdowns on the other sheets.
Schedule of Works |  | The task list: Task ID, Task, Trade, Predecessor Task ID, Duration (calendar days). Start, Finish, Status, and % Complete are calculated — nothing in those four columns needs to be typed in.
Gantt |  | A weekly grid Gantt chart. Task, Start, and Finish are pulled automatically from Schedule of Works; each week column is shaded wherever a task's date range overlaps that week.
Dashboard |  | A trade selector plus a snapshot of that trade's task count, total duration, and status breakdown, project-wide totals, and a full tasks-by-trade table.
How to use this workbook
1. Open Project Setup and enter your project name, project start date, and the "as of" date you want task status measured against. Edit the trade list if your job uses different trade categories.
2. Open Schedule of Works and list every task: give it a unique Task ID, a name, a Trade from the dropdown, a Duration in calendar days, and a Predecessor Task ID (leave it blank for the first task, or any task that starts on the project start date).
3. Check Start, Finish, Status, and % Complete on Schedule of Works — all four recalculate automatically from the predecessor chain and the "as of" date.
4. Open Gantt to see the weekly grid update — every task's shaded weeks are pulled directly from its calculated Start and Finish dates.
5. Go to Dashboard, pick a trade from the selector, and read that trade's task count, total duration, and status breakdown, or read the project totals and the full tasks-by-trade table below them.
Colour legend
Colour legend
Input — enter or edit your own data here
Calculated — formula-driven, please do not overwrite
Output — key result for reporting and dashboards
Using this workbook in Google Sheets
To use this workbook in Google Sheets: open Google Sheets, choose File > Import > Upload, select this .xlsx file, and choose "Insert new sheet(s)". Every formula in this workbook (SUM, SUMIF, SUMIFS, IF, IFERROR, INDEX, MATCH, ROUND, LARGE) is natively supported in Google Sheets, so no formula substitutions are required. Dropdown data validation on the trade selector and the Trade/Predecessor columns also carries over automatically.
Limitations
Every date in this workbook is calculated in calendar days, not working days — there is no WORKDAY-style weekend or holiday skipping, so a task scheduled over a weekend keeps running through it. Document your own crew's working-day calendar separately if that matters for your job. Each task supports exactly one predecessor: when two or more tasks must finish before the next one can start (for example, rough plumbing, electrical, and HVAC all finishing before insulation begins), point the Predecessor Task ID at whichever of them finishes latest — the workbook does not auto-detect that for you, so re-check it if you change an upstream duration. Schedule of Works column J is a hidden helper column (a constant 1 per row) that the Dashboard's SUMIF/SUMIFS formulas use to count tasks — don't delete it. Status and % Complete are both driven entirely by the "as of" date on Project Setup compared against each task's calculated Finish and Start, not by a separately tracked actual-progress field, so they reflect the plan, not field-reported progress. No macros, no external connections — everything here is a native formula, which is what keeps the workbook portable between Excel and Google Sheets with zero substitutions.
★ Free template from Excel.TV — get more free Excel & Google Sheets templates →

## Project Setup
Construction Schedule Template — Project Setup
Every date on Schedule of Works, Gantt, and Dashboard is chained from the Project Start Date below. Changing it (or the As Of Date) recalculates the entire schedule.
Project Name | Sample Custom Home Build
Project Start Date | 2026-03-02
As Of Date (task status below) | 2026-04-18
Trades
General Conditions
Sitework
Foundation
Framing
MEP
Finishes
Exterior

## Schedule of Works
Schedule of Works
Enter Task, Trade, Predecessor Task ID, and Duration for each task. Start, Finish, Status, and % Complete are calculated: Start = the predecessor's Finish + 1 calendar day (or the project start date with no predecessor), Finish = Start + Duration − 1, and Status/% Complete compare Start/Finish against the As Of Date on Project Setup.
Task ID | Task | Trade | Predecessor ID | Duration (days) | Start | Finish | Status | % Complete | Count
1 | Permits & Mobilization | General Conditions |  | 5 |  |  |  |  | 1
2 | Site Clearing & Grading | Sitework | 1 | 4 |  |  |  |  | 1
3 | Erosion & Sediment Control | Sitework | 1 | 2 |  |  |  |  | 1
4 | Foundation Excavation | Foundation | 2 | 3 |  |  |  |  | 1
5 | Footings & Foundation Walls | Foundation | 4 | 7 |  |  |  |  | 1
6 | Foundation Waterproofing & Backfill | Foundation | 5 | 3 |  |  |  |  | 1
7 | Rough Framing | Framing | 6 | 12 |  |  |  |  | 1
8 | Roof Sheathing & Dry-In | Framing | 7 | 5 |  |  |  |  | 1
9 | Rough Plumbing | MEP | 8 | 6 |  |  |  |  | 1
10 | Rough Electrical | MEP | 8 | 6 |  |  |  |  | 1
11 | Rough HVAC | MEP | 8 | 5 |  |  |  |  | 1
12 | Insulation | Finishes | 10 | 6 |  |  |  |  | 1
13 | Drywall Hang & Finish | Finishes | 12 | 8 |  |  |  |  | 1
14 | Interior Trim, Cabinetry & Paint | Finishes | 13 | 10 |  |  |  |  | 1
15 | Flooring | Finishes | 14 | 5 |  |  |  |  | 1
16 | Exterior Siding & Finishes | Exterior | 8 | 10 |  |  |  |  | 1
17 | Final Inspections & Punch List | General Conditions | 15 | 4 |  |  |  |  | 1

## Gantt
Construction Schedule — Weekly Gantt Grid
Task, Start, and Finish are pulled from Schedule of Works. Each week column header is the Monday that week starts on; a week is shaded for a task whenever that task's Start-to-Finish range overlaps that 7-day week.
Task ID | Task | Trade | Start | Finish

## Dashboard
Construction Schedule Template — Dashboard
As Of Date:
Filter by trade: | Framing
Selected trade — snapshot
Task Count
Total Duration (days)
Completed
In Progress
Not Started
Avg % Complete
Project totals — every trade
Project Start
Project Finish
Total Project Duration (days)
Total Tasks
Completed (project-wide)
In Progress (project-wide)
Not Started (project-wide)
Overall Avg % Complete
Tasks by trade
Trade | Task Count | Total Duration (days) | Completed | Avg % Complete
General Conditions
Sitework
Foundation
Framing
MEP
Finishes
Exterior
★ Free template from Excel.TV — get more free Excel & Google Sheets templates →