## Instructions
Project Budget Template
Purpose
This workbook tracks a project budget from planned budget to actual costs, committed costs, estimate-to-complete, estimate-at-completion, and a one-page financial summary. Replace the synthetic project, budget lines, cost log, and forecast inputs with your own project data; the workbook recalculates the variance and dashboard automatically.
Clean-room disclosure
Clean-room disclosure: every formula, layout, and sample figure in this workbook was authored from scratch for excel.tv. No vendor workbook, template, branding, report, connector behavior, or sample dataset was downloaded, inspected, or adapted in building this file. All project names, people, descriptions, and dollar amounts shown are synthetic and for illustration only.
What’s in this workbook
Project Setup |  | Project metadata, dates, contingency percentage, and review threshold used by the rest of the workbook.
Budget |  | The approved baseline budget by phase and category, with formulas that pull actual and committed spend from the Costs sheet.
Costs |  | A transaction-style cost log. Enter one actual or committed cost per row with date, phase, category, type, description, amount, and status.
Forecast to Complete |  | Combines original budget, actuals, committed costs, and an editable estimate-to-complete input to calculate EAC and variance at completion.
Project Summary |  | Dashboard-style output: total budget, actuals, commitments, ETC, EAC, variance, phase rollups, and the three largest category variances.
How to use this workbook
1. Open Project Setup and replace the sample project name, sponsor, project manager, dates, status, contingency percentage, and review threshold.
2. Open Budget and replace the phase/category rows with your own approved budget lines. Keep each category unique unless you also adjust the lookup formulas.
3. Open Costs and enter every actual invoice, internal charge, or committed purchase order as one row. Use the Phase, Category, Cost Type, and Status dropdowns to keep the formulas consistent.
4. Open Forecast to Complete and update the ETC Input column with the remaining spend you still expect for each category. Actual and committed amounts flow in from the Budget and Costs sheets.
5. Open Project Summary to review total estimate at completion, variance against the baseline budget, variance after contingency, phase-level rollups, and the three largest variance categories.
Colour legend
Colour legend
Input — enter or edit your own data here
Calculated — formula-driven, please do not overwrite
Output — key result for reporting and dashboards
Using this workbook in Google Sheets
To use this workbook in Google Sheets: open Google Sheets, choose File > Import > Upload, select this .xlsx file, and choose "Insert new sheet(s)." Every formula in this workbook (SUM, SUMIFS, IF, IFERROR, INDEX, MATCH, ABS, ROUND, LARGE, and arithmetic) is natively supported in Google Sheets, so no formula substitutions are required. Dropdown data validation for phase, category, cost type, status, and project status also carries over.
Limitations
The sample model assumes each budget category is unique and appears once in Budget and Forecast to Complete. If your project needs duplicate category names under different phases, use a combined phase/category key or expand the SUMIFS criteria before entering real data. The forecast is not a cash-flow model; it tracks cost-at-completion, not payment timing. The top-3 variance ranking uses LARGE + MATCH, which returns the first matching category when two categories have the same absolute variance. Contingency is shown as a management reserve on Project Summary; it does not automatically increase each category budget.
★ Free template from Excel.TV — get more free Excel & Google Sheets templates →

## Project Setup
Project Setup
Field | Input | Notes
Project Name | Northstar Client Portal Launch | Replace with the project or initiative name used in status reporting.
Sponsor | Operations Team | Business owner accountable for funding and scope decisions.
Project Manager | Avery Lin | Person maintaining this workbook and explaining the forecast.
Start Date | 2026-01-12 | Planned or actual project start date.
Target Finish Date | 2026-06-26 | Current planned finish date.
Project Status | In Progress | Use Not Started, In Progress, At Risk, or Complete.
Contingency % | 10% | Management reserve shown separately on the summary sheet.
Review Threshold | 5% | Variance percent threshold used to label tight or over-forecast categories.
Workbook rule: update blue input cells only. Yellow cells are formulas, and green cells are report outputs.
★ Free template from Excel.TV — get more free Excel & Google Sheets templates →

## Budget
Enter the approved budget by phase and category. Actual and committed costs are pulled from the Costs sheet, so this tab becomes the budget-vs-spend control table.
Phase | Category | Owner | Original Budget | Actual Spend | Committed | Remaining Budget | % Used | Status | Notes
Discovery | Research | Product | 12000 | [5 empty] | Customer interviews, workflow review, and requirements synthesis.
Discovery | Stakeholder Workshops | Operations | 4500 | [5 empty] | Working sessions with the implementation team and department leads.
Design | UX Design | Design | 18000 | [5 empty] | Wireframes, prototype review, and usability revisions.
Design | Creative Direction | Design | 9000 | [5 empty] | Visual design, icon set, and launch-ready interface polish.
Build | Engineering Labor | Engineering | 78000 | [5 empty] | Application build, integrations, permissions, and deployment support.
Build | Software Tools | Engineering | 8500 | [5 empty] | Temporary development tooling, testing utilities, and sandbox licenses.
Build | QA Testing | Quality | 15000 | [5 empty] | Regression testing, accessibility checks, and launch acceptance testing.
Launch | Training | Enablement | 7000 | [5 empty] | Admin training, internal job aids, and live handoff sessions.
Launch | Launch Collateral | Marketing | 12000 | [5 empty] | Help-center articles, launch email sequence, and stakeholder materials.
Project Management | Project Management | PMO | 22000 | [5 empty] | Schedule coordination, status reporting, risk log, and budget governance.
Baseline budget total

## Costs
Enter one project cost per row. Cost Type drives the formulas: Actual means already incurred; Committed means approved or contracted but not yet fully spent.
Date | Phase | Category | Cost Type | Description | Amount | Status | Notes
2026-01-19 | Discovery | Research | Actual | Interview planning and first research sprint | 8200 | Approved
2026-01-28 | Discovery | Stakeholder Workshops | Actual | Two cross-functional workshop sessions | 3600 | Approved
2026-02-12 | Design | UX Design | Actual | Prototype design sprint | 12800 | Approved
2026-02-26 | Design | Creative Direction | Actual | Visual system and UI production pass | 7600 | Approved
2026-03-15 | Build | Engineering Labor | Actual | Portal foundation and authentication work | 44250 | Approved
2026-03-22 | Build | Software Tools | Actual | Sandbox and QA utility licenses | 5100 | Approved
2026-04-06 | Build | QA Testing | Actual | First regression testing cycle | 9200 | Approved
2026-04-18 | Launch | Training | Actual | Administrator training dry run | 4200 | Approved
2026-04-25 | Project Management | Project Management | Actual | PMO support through build checkpoint | 9800 | Approved
2026-05-02 | Build | Engineering Labor | Committed | Remaining integration contract | 18500 | Committed
2026-05-05 | Build | Software Tools | Committed | Final month of testing utilities | 2400 | Committed
2026-05-10 | Launch | Launch Collateral | Committed | Launch content package | 6300 | Committed
2026-05-12 | Launch | Training | Committed | Facilitator support for go-live sessions | 1800 | Committed

## Forecast to Complete
Update ETC Input for the remaining spend you still expect. Actual and committed costs flow in from Budget/Costs; EAC and variance calculate automatically.
Phase | Category | Original Budget | Actual Spend | Committed | ETC Input | EAC | Variance at Completion | Variance % | Abs Variance | Status
0
0
3200
900
38000
1400
5200
2800
7400
7200
Forecast total

## Project Summary
Project Budget Summary
Project
Status
Metric | Amount | Notes
Original Budget |  | Approved baseline before contingency.
Contingency Reserve |  | Separate management reserve, not spread across categories.
Approved Budget incl. Contingency |  | Baseline plus contingency reserve.
Actual Spend |  | Costs already incurred.
Committed Costs |  | Approved or contracted costs not fully spent yet.
Estimate to Complete |  | Remaining forecast entered by the project owner.
Estimate at Completion |  | Actual plus committed plus remaining ETC.
Variance vs. Original Budget |  | Positive is under budget; negative is over budget.
Remaining After Contingency |  | Positive means contingency still covers the forecast.
Phase rollup
Phase | Budget | Actual + Committed | ETC | EAC | Variance
Discovery
Design
Build
Launch
Project Management
Top 3 variance categories (by absolute variance at completion)
Rank | Category | Abs Variance | Variance $
1
2
3
★ Free template from Excel.TV — get more free Excel & Google Sheets templates →