## Instructions
Project Tracker Template
Purpose
This workbook helps one person or a small team run several projects at once. List your projects, list the tasks under each one with planned hours and due dates, and the workbook rolls everything up: hours-weighted percent complete per project, overdue and due-soon task flags measured against an as-of date you control, workload by team member, and a one-page portfolio dashboard. Replace the synthetic sample projects and tasks with your own; every calculated sheet recalculates automatically.
Clean-room disclosure
Clean-room disclosure: every formula, layout, instruction, and sample figure in this workbook was authored from scratch for Excel.TV. No vendor workbook, gated template, branding, connector behavior, or sample dataset was downloaded, inspected, mirrored, transformed, or adapted in building this file. All data shown is synthetic and for illustration only.
What’s in this workbook
Projects |  | One row per project: ID, name, owner, start and due dates, and a status you pick (Active, On Hold, Complete). It also holds the As Of Date input in B2. Calculated columns show task counts, planned and done hours, percent complete, time elapsed, overdue tasks, days to due, and a Red / Amber / Green rating.
Tasks |  | One row per task: task ID, project ID, task name, owner, the task it depends on, planned hours, a Done Yes/No flag, and a due date. Calculated columns show days overdue, status, due-soon flag, whether the dependency is clear, and how many open tasks are waiting on this one.
Team |  | One row per person with weekly capacity in hours. Calculated columns total open tasks, open hours, overdue tasks, hours that fall due in the next 14 days (overdue work included), and a load rating against two weeks of capacity.
Dashboard |  | The one-page output: project counts by rating, portfolio percent complete, overdue and due-soon tasks, overdue tasks that block other work, overloaded people, the portfolio table, and the five most overdue tasks.
How to use this workbook
1. Open Projects and replace the sample projects with your own. Keep each Project ID unique because Tasks and the roll-ups use it as the lookup key.
2. Set the As Of Date in Projects B2. Every overdue and due-soon flag is measured against that date, not today, so you can review any week by changing one cell.
3. Open Team and list the people who own tasks, with the project hours each can give per week.
4. Open Tasks and enter your tasks. Give each one a project ID, an owner from the Team list, planned hours, a due date, and the ID of the task it depends on if there is one. Change Done? to Yes when the work is finished.
5. Review Projects for the Red / Amber / Green rating, Team for who is overloaded, and Dashboard for the one-page summary.
Colour legend
Colour legend
Input — enter or edit your own data here
Calculated — formula-driven, please do not overwrite
Output — key result for reporting and dashboards
Using this workbook in Google Sheets
To use this workbook in Google Sheets: open Google Sheets, choose File > Import > Upload, select this .xlsx file, and choose Insert new sheet(s). The workbook uses Google Sheets-compatible formulas only: SUM, SUMIF, SUMIFS, COUNTIF, COUNTIFS, IF, IFERROR, AND, OR, MIN, MAX, INDEX, MATCH, LARGE, ROW, and arithmetic. Dropdown validation for status, owner, project ID, and the Done flag carries over during import, and the Red / Amber / Green colors are conditional formatting that you should glance at after import.
Limitations
This template is a spreadsheet tracker, not a project-management application. It does not send reminders, store files, track time against tasks, or draw a Gantt chart, and it does not calculate a critical path: the Depends On column shows which open tasks are waiting on which, and you decide what that means for the schedule. Percent complete is weighted by planned hours, so it is only as accurate as your hour estimates. The Red / Amber / Green rule is one simple choice (overdue tasks and the gap between percent complete and time elapsed); edit the formula on Projects if your team rates projects differently. Formula ranges are sized to the sample data, so when you add projects, tasks, or people, copy the formulas down and extend the ranges. The overdue ranking breaks ties by row order.
★ Free template from Excel.TV — get more free Excel & Google Sheets templates →

## Projects
List each project in the blue cells. Set the As Of Date in B2: every overdue, due-soon, and Red / Amber / Green result in this workbook is measured against it. Yellow columns are calculated from the Tasks sheet.
As Of Date: | 2026-10-05
Project ID | Project Name | Owner | Start Date | Due Date | Status | Tasks | Planned Hours | Done Hours | % Complete | Time Elapsed % | Overdue Tasks | Days to Due | Rating
P-101 | Website Refresh | Maria Lopez | 2026-08-10 | 2026-11-20 | Active
P-102 | CRM Migration | Devon Clark | 2026-09-01 | 2026-12-11 | Active
P-103 | Q4 Event Launch | Priya Shah | 2026-09-14 | 2026-11-06 | Active
P-104 | Office Move | Sam Okafor | 2026-08-24 | 2026-10-16 | Active
P-105 | Annual Audit Prep | Maria Lopez | 2026-07-13 | 2026-09-25 | Complete
P-106 | Training Rollout | Devon Clark | 2026-10-19 | 2027-01-29 | On Hold

## Tasks
Enter one task per row in the blue cells. Days Overdue, Status, and the flags are measured against the As Of Date on Projects B2. Depends On is optional: enter the Task ID that must finish first. Hidden columns R and S are helpers used by the roll-ups.
Task ID | Project ID | Project Name | Task | Owner | Depends On | Planned Hours | Done? (Yes/No) | Due Date | Done Hours | Days Overdue | Status | Overdue Flag | Due Soon Flag | Dependency | Open Tasks Waiting On This | Blocking Overdue Flag | Overdue Sort Key | Count Helper
T-101 | P-101 |  | Content inventory | Maria Lopez |  | 8 | Yes | 2026-08-21
T-102 | P-101 |  | Wireframes | Jordan Reyes | T-101 | 16 | Yes | 2026-09-04
T-103 | P-101 |  | Page templates build | Devon Clark | T-102 | 24 | Yes | 2026-09-25
T-104 | P-101 |  | Content migration | Maria Lopez | T-103 | 20 | No | 2026-10-09
T-105 | P-101 |  | QA and redirects | Jordan Reyes | T-104 | 12 | No | 2026-10-30
T-106 | P-101 |  | Launch day checklist | Devon Clark | T-105 | 6 | No | 2026-11-20
T-201 | P-102 |  | Field mapping | Devon Clark |  | 10 | Yes | 2026-09-18
T-202 | P-102 |  | Data cleanup | Sam Okafor | T-201 | 18 | No | 2026-10-02
T-203 | P-102 |  | Pilot import | Devon Clark | T-202 | 8 | No | 2026-10-23
T-204 | P-102 |  | User training | Priya Shah | T-203 | 10 | No | 2026-11-20
T-205 | P-102 |  | Cutover weekend | Devon Clark | T-204 | 12 | No | 2026-12-11
T-301 | P-103 |  | Book venue | Priya Shah |  | 6 | Yes | 2026-09-25
T-302 | P-103 |  | Send speaker invites | Priya Shah | T-301 | 4 | Yes | 2026-09-28
T-303 | P-103 |  | Registration page | Jordan Reyes | T-301 | 12 | No | 2026-09-30
T-304 | P-103 |  | Promo email series | Maria Lopez | T-303 | 10 | No | 2026-10-11
T-305 | P-103 |  | Run of show | Priya Shah | T-304 | 8 | No | 2026-10-30
T-401 | P-104 |  | Space plan | Sam Okafor |  | 8 | Yes | 2026-09-04
T-402 | P-104 |  | Vendor quotes | Sam Okafor | T-401 | 6 | Yes | 2026-09-11
T-403 | P-104 |  | Network and phone setup | Jordan Reyes | T-402 | 20 | No | 2026-10-01
T-404 | P-104 |  | Pack and label | Priya Shah | T-402 | 14 | No | 2026-10-02
T-405 | P-104 |  | Move day | Sam Okafor | T-403 | 10 | No | 2026-10-16
T-501 | P-105 |  | Collect records | Maria Lopez |  | 10 | Yes | 2026-08-07
T-502 | P-105 |  | Reconcile accounts | Maria Lopez | T-501 | 14 | Yes | 2026-09-04
T-503 | P-105 |  | Auditor walkthrough | Jordan Reyes | T-502 | 6 | Yes | 2026-09-22
T-601 | P-106 |  | Curriculum draft | Priya Shah |  | 12 | No | 2026-11-13
T-602 | P-106 |  | Pilot session | Devon Clark | T-601 | 6 | No | 2026-12-04

## Team
List each person and the hours per week they can give to these projects. Load compares the open hours due in the next 14 days (overdue work included) with two weeks of capacity. A person with work due but no capacity entered shows No capacity and is rated Over.
Name | Role | Weekly Capacity (hrs) | Open Tasks | Open Hours | Overdue Tasks | Hours Due in 14 Days | Load % of 2 Weeks | Load
Maria Lopez | Content lead | 20
Devon Clark | Systems lead | 20
Priya Shah | Programs manager | 16
Sam Okafor | Operations | 12
Jordan Reyes | Web developer | 20

## Dashboard
Project Tracker Template
As of date:
Portfolio summary
Metric | Result | How it is calculated
Active projects |  | Projects on the Projects sheet with Status set to Active.
Red projects |  | Two or more overdue tasks, a past-due project, or percent complete more than 25 points behind time elapsed.
Amber projects |  | One overdue task, or percent complete more than 10 points behind time elapsed.
Portfolio % complete |  | All done hours divided by all planned hours across every project.
Open tasks |  | Tasks on the Tasks sheet where Done? is No.
Overdue tasks |  | Open tasks with a due date before the as-of date.
Due in next 7 days |  | Open tasks due within 7 days of the as-of date and not already overdue.
Overdue tasks blocking other work |  | Overdue tasks that at least one other open task lists in Depends On.
People over capacity |  | Team members whose hours due in 14 days exceed two weeks of capacity.
Projects at a glance
Project | Owner | % Complete | Overdue Tasks | Days to Due | Rating
Most overdue tasks
Task | Project | Owner | Days Overdue | Tasks Waiting On It
★ Free template from Excel.TV — get more free Excel & Google Sheets templates →